## Project Budget
No. | Item | Details | Cost type | Qty | Unit | Rate (Rs.) | Duration / hours | Total (Rs.)
Personnel
1 | Project management and documentation (Laiba) | SPMP, reports, supervisor meetings | In-kind | 1 | hours | 450 | 90 | 40500
2 | Requirements, UI mockups and SRS (Laiba) | User classes, mockups M1 to M10, SRS | In-kind | 1 | hours | 450 | 90 | 40500
3 | Frontend development, Flutter app (Laiba) | Desktop app screens and integration | In-kind | 1 | hours | 450 | 190 | 85500
4 | System design (Waris) | Architecture, UML, database design | In-kind | 1 | hours | 600 | 50 | 30000
5 | Dataset collection and labelling (Waris) | AI-generated Express apps and CWE labels | In-kind | 1 | hours | 600 | 90 | 54000
6 | Model fine-tuning and evaluation (Waris) | CodeBERT / GraphCodeBERT, calibration | In-kind | 1 | hours | 600 | 90 | 54000
7 | Scan engine, fixes and export (Waris) | Parser, route analyzer, rules, fixes, PDF and SARIF | In-kind | 1 | hours | 600 | 140 | 84000
8 | Supervisor guidance | Provided by the university, not charged | In-kind | 1 | hours | 0 | 0 | 0
| Subtotal - Personnel | [6 empty] | 388500
Software and Development Tools
9 | Flutter, Dart, VS Code, Visual Studio Community | Desktop app development | Free | 1 | set | 0 | 1 | 0
10 | Python, PyTorch, Hugging Face Transformers | Model training and running on CPU | Free | 1 | set | 0 | 1 | 0
11 | Tree-sitter, SQLite, Node.js, Express | Parsing, local database, sample apps | Free | 1 | set | 0 | 1 | 0
12 | Git, GitHub, ClickUp, draw.io, Google Docs | Version control, planning, diagrams, documents | Free | 1 | set | 0 | 1 | 0
13 | Semgrep, Gitleaks, PyInstaller, Inno Setup | Baseline tools for evaluation, installer | Free | 1 | set | 0 | 1 | 0
| Subtotal - Software and Development Tools | [6 empty] | 0
Hardware and Infrastructure
14 | Developer laptops (owned) | Depreciation = value / useful life per month | In-kind | 2 | laptops | 2708.3333 | 7 | 37916.6667
15 | Home internet | Already paid by each student | In-kind | 2 | students | 3500 | 7 | 49000
16 | External backup drive, 1 TB | Backup of dataset, model files, documents | Cash | 1 | drive | 14000 | 1 | 14000
| Subtotal - Hardware and Infrastructure | [6 empty] | 100916.6667
Cloud Computing and Model Training
17 | Google Colab and Kaggle free GPU | Model fine-tuning on free tier | Free | 1 | service | 0 | 1 | 0
18 | Google Colab Pro, 2 months | In case the free GPU limit is not enough | Cash | 1 | subscription | 2800 | 2 | 5600
19 | Google Drive free storage | Checkpoints and backups | Free | 1 | service | 0 | 1 | 0
20 | Cloud hosting for the product | Not needed: LYKOS runs on the user's computer | Free | 0 | service | 0 | 1 | 0
| Subtotal - Cloud Computing and Model Training | [6 empty] | 5600
Testing and Quality Assurance
21 | Testing effort (Laiba) | Test plan, test cases, usability test | In-kind | 1 | hours | 400 | 50 | 20000
22 | Testing effort (Waris) | Unit, integration and performance tests | In-kind | 1 | hours | 400 | 50 | 20000
23 | pytest, flutter_test, SonarQube Community, Ruff | Test frameworks and code analysis | Free | 1 | set | 0 | 1 | 0
24 | Usability test refreshments | 5 volunteer testers | Cash | 5 | persons | 500 | 1 | 2500
| Subtotal - Testing and Quality Assurance | [6 empty] | 42500
Documentation, Printing and Travel
25 | Final report printing and binding | 4 copies | Cash | 4 | copies | 1500 | 1 | 6000
26 | Poster printing | Final presentation | Cash | 1 | poster | 2000 | 1 | 2000
27 | Travel to university | Supervisor meetings and demos, one trip every 2 weeks per student | Cash | 2 | students | 400 | 14 | 11200
| Subtotal - Documentation, Printing and Travel | [6 empty] | 19200
| Total of all categories (before contingency) | [6 empty] | 556716.6667

## Cost Summary
Cost category | Total (Rs.) | Cash (Rs.) | In-kind (Rs.) | Share of total
Personnel | 388500 | 0 | 388500 | 69.78%
Software and Development Tools | 0 | 0 | 0 | 0%
Hardware and Infrastructure | 100916.6667 | 14000 | 86916.6667 | 18.13%
Cloud Computing and Model Training | 5600 | 5600 | 0 | 1.006%
Testing and Quality Assurance | 42500 | 2500 | 40000 | 7.634%
Documentation, Printing and Travel | 19200 | 19200 | 0 | 3.449%
Project subtotal | 556716.6667 | 41300 | 515416.6667 | 100%
Contingency | 55671.6667 | 4130 | 51541.6667 | 10%
Final project budget (with contingency) | 612388.3333 | 45430 | 566958.3333
Cash needed per student (with contingency) | 22715
Budget per working day | 4469.9878
Planned student hours | 840
Available student hours | 840

## Assumptions
Assumption | Value | Note
Project start date | 2026-11-02 | As per the project schedule
Project end date | 2027-05-11 | Final delivery milestone
Working days (Mon to Fri) | 137 | Public holidays not removed
Working weeks | 28 | Working days / 5
Months (rounded up) | 7 | Used for depreciation and internet
Team members | 2 | Laiba and Waris
Hours per student per week | 15 | Effort alongside other courses
Exchange rate (Rs. per USD) | 280 | Approximate; used for USD prices
Contingency (% of subtotal) | 10% | For unexpected costs and estimation errors
Hourly rate: Flutter / frontend developer | 450 | Approximate junior rate in Pakistan
Hourly rate: backend / ML engineer | 600 | Approximate junior rate in Pakistan
Hourly rate: project manager / analyst | 450 | Approximate junior rate
Hourly rate: tester / QA | 400 | Approximate junior rate
Laptop value (each) | 130000 | Both laptops are already owned
Laptop useful life (months) | 48 | Straight-line depreciation
Internet per student per month | 3500 | Already paid by each student
External backup drive, 1 TB | 14000 | Shop price estimate
Google Colab Pro (USD per month) | 10 | Only if free GPU limits are not enough
Refreshments per usability tester | 500 | Tea and snacks
Report printing and binding (per copy) | 1500 | Print shop estimate
Poster printing | 2000 | Print shop estimate
Travel to university per trip | 400 | Local transport, one student, one way plus return
Formulas:
Value = NETWORKDAYS(B2,[Value, row above])